## Gantt Chart
POS Application · Development Sprint · 28 Feb – 8 Mar 2026 · 2 Developers · ALL TASKS COMPLETE ✅
| ✅ Done |  | 🎨 Holi Day (12 h) |  | 🏋 Extra Saturday (12 h) |  | Dev 1 – UI / Design |  | Dev 2 – Functionality |  | Both Developers
# | Task / Feature | Developer | Est. Hrs | Actual Hrs | Priority | Start | End | Sat 28 Feb | Sun 01 Mar | Mon 02 Mar | Tue 03 Mar | Wed 04 Mar 🎨 Holi | Thu 05 Mar | Fri 06 Mar | Sat 07 Mar | Sun 08 Mar
RESPONSIVE UI — Dev 1
1 | ✅ Mobile Phone Layout All screens – portrait & landscape | Dev 1 (UI) | 14h | 14h | High | 28 Feb | 01 Mar | ✅ Mobile Phone Layou
2 | ✅ Small Tablet Layout (Galaxy A9 / 8–9 inch) 600–799dp breakpoint – all screens | Dev 1 (UI) | 14h | 14h | High | 02 Mar | 03 Mar |  |  | ✅ Small Tablet Layou
3 | ✅ Large Tablet Layout (10 inch +) Landscape optimised, side-by-side panels | Dev 1 (UI) | 12h | 12h | High | 04 Mar | 05 Mar |  |  |  |  | ✅ Large Tablet Layou
UI IMPROVEMENTS — Dev 1
4 | ✅ POS & Order Screen UI Item grid, cart panel, status cards | Dev 1 (UI) | 8h | 8h | Medium | 06 Mar | 06 Mar | [6 empty] | ✅ POS & Order Screen
5 | ✅ Area & Table Selection Area tabs on table picker screen | Dev 1 (UI) | 4h | 4h | Medium | 07 Mar | 07 Mar | [7 empty] | ✅ Area & Table Selec
6 | ✅ Printer Screen UI Print buttons, receipt preview, IP inputs styled | Dev 1 (UI) | 7h | 7h | Medium | 07 Mar | 08 Mar | [7 empty] | ✅ Printer Screen UI
7 | ✅ Final UI Polish & Review | Dev 1 (UI) | 3h | 3h | Low | 08 Mar | 08 Mar | [8 empty] | ✅ Final UI Polish &
PAYMENT & BILLING — Dev 2
8 | ✅ Order Number Display Fix Correct order ID shown on all screens | Dev 2 (Func) | 3h | 3h | High | 28 Feb | 28 Feb | ✅ Order Number Displ
9 | ✅ Cash Payment Flow Full checkout with change calculation | Dev 2 (Func) | 7h | 7h | Critical | 28 Feb | 01 Mar | ✅ Cash Payment Flow
10 | ✅ Card Payment via Terminal Approval from TRX payment terminal | Dev 2 (Func) | 7h | 7h | Critical | 01 Mar | 02 Mar |  | ✅ Card Payment via T
11 | ✅ Split Payment – Card + Cash Mixed payment methods on single bill | Dev 2 (Func) | 7h | 7h | Critical | 02 Mar | 03 Mar |  |  | ✅ Split Payment –
12 | ✅ Split Equally (2 & 3 Guests) Per-guest equal share | Dev 2 (Func) | 7h | 7h | High | 03 Mar | 04 Mar |  |  |  | ✅ Split Equally (2
13 | ✅ Split by Items Items assigned to specific guests | Dev 2 (Func) | 6h | 6h | High | 04 Mar | 04 Mar |  |  |  |  | ✅ Split by Items
14 | ✅ Combine Bills Merge two open table bills into one | Dev 2 (Func) | 6h | 6h | High | 04 Mar | 05 Mar |  |  |  |  | ✅ Combine Bills
FUNCTIONALITY — Dev 2
15 | ✅ Discount & Promotions % or fixed amount discount at checkout | Dev 2 (Func) | 16h | 14h | High | 05 Mar | 07 Mar | [5 empty] | ✅ Discount & Promoti
16 | ✅ Live Activity Logs Real-time manager view of order activity | Dev 2 (Func) | 6h | 5h | Medium | 07 Mar | 08 Mar | [7 empty] | ✅ Live Activity Logs
17 | ✅ Bill Transfer Move items between two open bills | Dev 2 (Func) | 5h | 5h | Medium | 07 Mar | 08 Mar | [7 empty] | ✅ Bill Transfer
RECEIPT PRINTING — Both Developers
18 | ✅ Receipt & KOT Printing – Full Integration ESC/POS TCP, PrinterContext, per-station routing | Both | 20h | 22h | High | 04 Mar | 08 Mar |  |  |  |  | ✅ Receipt & KOT Prin
TESTING & HANDOFF — Both Developers
19 | ✅ Payment & Billing Testing All payment flows verified end-to-end | Both | 6h | 6h | High | 03 Mar | 05 Mar |  |  |  | ✅ Payment & Billing
20 | ✅ UI Testing – All Device Sizes Phone, Galaxy A9, large tablet | Both | 6h | 6h | High | 06 Mar | 08 Mar | [6 empty] | ✅ UI Testing – All D
21 | ✅ Testing & Bug Fixes Cross-feature final fixes | Both | 5h | 5h | High | 07 Mar | 08 Mar | [7 empty] | ✅ Testing & Bug Fixe
22 | ✅ Client Demo & Handoff Walkthrough and sign-off | Both | 4h | 4h | Critical | 08 Mar | 08 Mar | [8 empty] | ✅ Client Demo & Hand
Dev 1 (UI) – Daily Hours | [7 empty] | 12h | 7h | 8h | 8h | 12h | 7h | 8h | 12h | 7h
Dev 2 (Func) – Daily Hours | [7 empty] | 12h | 8h | 8h | 8h | 12h | 8h | 8h | 12h | 8h
Sprint: 28 Feb – 8 Mar 2026 (9 days) ¦ Dev 1 (UI): 81h ¦ Dev 2 (Functionality): 84h ¦ Holi 🎨 4 Mar + Extra Sat 28 Feb & 7 Mar = 12h/dev ¦ Tasks: 22 ✅ ALL COMPLETE

## Test Cases
POS Application · QA Test Cases · Sprint 28 Feb – 8 Mar 2026 · ✅ 30/30 PASS
TC # | Test Name | Feature Area | Test Type | Result | What Is Verified
── MENU SETUP ─────────────────────────────────────────────────────────────────
TC-01 | Menu Categories Setup | Menu Management | Functional | PASS | Create 3 categories (Drinks, Mains, Starters) — visible in POS with correct grouping
TC-02 | Add Menu Items | Menu Management | Functional | PASS | 6 items added with name, price and category — all appear correctly in POS ordering screen
TC-03 | Modifier Groups | Menu Management | Functional | PASS | Modifier groups created with multiple options — displayed at checkout when item tapped
TC-04 | Assign Modifiers to Items | Menu Management | Functional | PASS | Modifiers linked to menu items — correct options appear when ordering that item
── ORDERING ────────────────────────────────────────────────────────────────────
TC-05 | POS – Portrait Mode | POS Ordering | End-to-End | PASS | Select table → tap item → choose modifier → add to cart → send to kitchen — all steps complete
TC-06 | POS – Landscape Mode | POS Ordering | End-to-End | PASS | Same order flow in landscape orientation — layout adjusts, no buttons cut off
TC-07 | Kitchen Display Flow | Kitchen | End-to-End | PASS | Order appears in kitchen → staff progresses status → order marked Served in Order Management
TC-08 | Cancel Order – Kitchen Sync | Kitchen / Orders | Functional | PASS | Cancelling an order removes it from kitchen display immediately
TC-09 | Kitchen Station Settings | Settings | Functional | PASS | Add, rename and delete kitchen stations — changes visible in kitchen display
TC-10 | Item Routing to Station | Kitchen / Menu | Functional | PASS | Setting a station on a menu item sends that item to the correct kitchen station
── PAYMENT ─────────────────────────────────────────────────────────────────────
TC-11 | Cash Payment | Payment | End-to-End | PASS | Served order → Pay → enter cash → change calculated → order marked Paid
TC-12 | Full Bill Pay via Bill Screen | Payment | End-to-End | PASS | Bill screen opened → Pay Full Bill tapped → payment confirmed → order Paid
TC-13 | Card Payment via Terminal | Payment | End-to-End | PASS | Card payment sent to payment terminal — approval received — order marked Paid
TC-14 | Terminal Save & Reconnect | Payment | Functional | PASS | Terminal details saved — after app restart terminal reconnects without re-entering IP
── SPLIT BILL ──────────────────────────────────────────────────────────────────
TC-15 | Split Equally – 2 Guests | Split Bill | End-to-End | PASS | Bill divided equally between 2 guests — each guest pays their share independently
TC-16 | Split Equally – 3 Guests | Split Bill | End-to-End | PASS | 3-way equal split — all 3 guests pay — order marked Paid when all confirmed
TC-17 | Split by Items | Split Bill | End-to-End | PASS | Specific items assigned to each guest — guests pay only for their items
TC-18 | Multiple Payment Methods | Payment | End-to-End | PASS | Single bill paid across multiple payment entries — total matched — order Paid
TC-19 | Split – Card + Cash | Payment | End-to-End | PASS | Card portion processed via terminal, cash portion applied — combined total confirmed, order Paid
── COMBINE BILLS ───────────────────────────────────────────────────────────────
TC-20 | Combine Two Bills | Billing | End-to-End | PASS | Combine Bills button → select another table's order → orders merged → source order closed
── DATA PERSISTENCE ────────────────────────────────────────────────────────────
TC-21 | Data Saved After App Restart | Data Storage | Functional | PASS | Force-close and reopen app — all orders, menu items, payment status restored
── RESPONSIVE UI ───────────────────────────────────────────────────────────────
TC-22 | Mobile Phone – All Screens | Responsive UI | UI Testing | PASS | All app screens checked on phone size — portrait and landscape, correct layout and no overflow
TC-23 | Small Tablet – Galaxy A9 | Responsive UI | UI Testing | PASS | All screens on Galaxy A9 tablet — correct grid columns, touch targets, sidebar behaviour
TC-24 | Large Tablet – 10 inch+ | Responsive UI | UI Testing | PASS | All screens on 10 inch tablet in landscape — side panel pinned, multi-column layout correct
── RECEIPT & KOT PRINTING ─────────────────────────────────────────────────
TC-25 | Receipt Printer Settings | Printer Settings | Functional | PASS | IP, port, paper size saved — persists after app restart
TC-26 | Print Test Page | Printer Settings | Functional | PASS | Test Page button sends ESC/POS bytes to printer IP — success toast shown
TC-27 | KOT – Single Kitchen Printer | Printing | End-to-End | PASS | No station printers set — all items printed as one consolidated ticket to default kitchen printer
TC-28 | KOT – Per-Station Routing | Printing | End-to-End | PASS | Hot Kitchen + Bar printers set — items routed to correct station printer; unassigned items fall back to default
TC-29 | Kitchen Display Reprint | Kitchen / Printing | Functional | PASS | Reprint button on kitchen ticket card re-sends KOT for that station
TC-30 | Receipt Print on Payment | Payment / Printing | End-to-End | PASS | Payment confirmed → receipt printed to receipt printer via ESC/POS TCP
Total: 30 test cases ¦ Passed: 30 ¦ Failed: 0 ¦ Pass Rate: 100% ✅

## Progress Summary
POS Application · Feature Status · Sprint 28 Feb – 8 Mar 2026 · ✅ ALL COMPLETE
Feature | Status | Est. Hrs | Actual Hrs | Notes
── RESPONSIVE UI ──────────────────────────────────────────
Mobile Phone Layout | ✅ Done | 14h | 14h | Portrait & landscape – all screens
Small Tablet Layout (Galaxy A9) | ✅ Done | 14h | 14h | 600–799dp – all screens
Large Tablet Layout (10 inch +) | ✅ Done | 12h | 12h | Landscape side-by-side panels
── UI IMPROVEMENTS ────────────────────────────────────────
POS & Order Screen Updates | ✅ Done | 8h | 8h | Item grid, cart panel refinements
Area & Table Selection | ✅ Done | 4h | 4h | Area tabs on table picker
Printer Screen UI (IP inputs styled) | ✅ Done | 7h | 7h | Input borders + background added
Final Polish & Review | ✅ Done | 3h | 3h | Cross-device final check
── PAYMENT & BILLING ──────────────────────────────────────
Order Number Display Fix | ✅ Done | 3h | 3h | Order number on all screens
Cash Payment Flow | ✅ Done | 7h | 7h | Full flow with change calculation
Card Payment via Terminal | ✅ Done | 7h | 7h | TRX terminal approval working
Split Payment – Card + Cash | ✅ Done | 7h | 7h | Mixed payment on single bill
Split Equally (2 & 3 Guests) | ✅ Done | 7h | 7h | Per-guest equal share
Split by Items | ✅ Done | 6h | 6h | Items assigned per guest
Combine Bills | ✅ Done | 6h | 6h | Merge two open bills
── FUNCTIONALITY ──────────────────────────────────────────
Discount & Promotions | ✅ Done | 16h | 14h | % or fixed at checkout
Live Activity Logs | ✅ Done | 6h | 5h | Real-time log updates
Bill Transfer | ✅ Done | 5h | 5h | Move items between open bills
── PRINTING ───────────────────────────────────────────────
Receipt & KOT Printing | ✅ Done | 20h | 22h | ESC/POS TCP + PrinterContext + station routing
── TESTING & HANDOFF ──────────────────────────────────────
Payment & Billing Testing | ✅ Done | 6h | 6h | All payment flows verified
UI Testing – All Device Sizes | ✅ Done | 6h | 6h | Phone, Galaxy A9, tablet
Testing & Bug Fixes | ✅ Done | 5h | 5h | Cross-feature final fixes
Client Demo & Handoff | ✅ Done | 4h | 4h | Walkthrough and sign-off
Sprint Total ¦ Dev 1 (UI): 81h ¦ Dev 2 (Func): 84h ¦ Combined: 165h ¦ Holi 🎨 + Extra Saturdays = +12h days ¦ 22 tasks ✅ DONE ¦ 0 pending