## Gantt Chart
POS Application · Development Sprint · 28 Feb – 8 Mar 2026 · 2 Developers
| 🔵 In Progress |  | 🟠 Planned |  |  |  | Dev 1 – UI / Design |  | Dev 2 – Functionality |  | Both Developers
# | Task / Feature | Developer | Est. Hrs | Priority | Status | Start | End | Sat 28 Feb | Sun 01 Mar | Mon 02 Mar | Tue 03 Mar | Wed 04 Mar | Thu 05 Mar | Fri 06 Mar | Sat 07 Mar | Sun 08 Mar
RESPONSIVE UI — Dev 1
1 | 🔵 Mobile Phone Layout All screens – portrait & landscape | Dev 1 (UI) | 14h | High | In Progress | 28 Feb | 01 Mar | Mobile Phone L
2 | 🔵 Small Tablet Layout (Galaxy A9 / 8–9 inch) 600–799dp breakpoint – all screens | Dev 1 (UI) | 14h | High | In Progress | 02 Mar | 03 Mar |  |  | Small Tablet L
3 | 🟠 Large Tablet Layout (10 inch +) Landscape optimised, side-by-side panels | Dev 1 (UI) | 12h | High | Planned | 04 Mar | 05 Mar |  |  |  |  | Large Tablet L
UI IMPROVEMENTS — Dev 1
4 | 🟠 POS & Order Screen UI Item grid, cart panel, status cards | Dev 1 (UI) | 8h | Medium | Planned | 06 Mar | 06 Mar | [6 empty] | POS & Order Sc
5 | 🟠 Area & Table Selection Area tabs on table picker screen | Dev 1 (UI) | 4h | Medium | Planned | 07 Mar | 07 Mar | [7 empty] | Area & Table S
6 | 🟠 Printer Screen UI Print buttons, receipt preview | Dev 1 (UI) | 7h | Medium | Planned | 07 Mar | 08 Mar | [7 empty] | Printer Screen
7 | 🟠 Final UI Polish & Review | Dev 1 (UI) | 3h | Low | Planned | 08 Mar | 08 Mar | [8 empty] | Final UI Polis
PAYMENT & BILLING — Dev 2
8 | 🔵 Order Number Display Fix Correct order ID shown on all screens | Dev 2 (Func) | 3h | High | In Progress | 28 Feb | 28 Feb | Order Number D
9 | 🔵 Cash Payment Flow Full checkout with change calculation | Dev 2 (Func) | 7h | Critical | In Progress | 28 Feb | 01 Mar | Cash Payment F
10 | 🔵 Card Payment via Terminal Approval from payment terminal | Dev 2 (Func) | 7h | Critical | In Progress | 01 Mar | 02 Mar |  | Card Payment v
11 | 🔵 Split Payment – Card + Cash Mixed payment methods on single bill | Dev 2 (Func) | 7h | Critical | In Progress | 02 Mar | 03 Mar |  |  | Split Payment
12 | 🔵 Split Equally (2 & 3 Guests) Per-guest equal share | Dev 2 (Func) | 7h | High | In Progress | 03 Mar | 03 Mar |  |  |  | Split Equally
13 | 🔵 Split by Items Items assigned to specific guests | Dev 2 (Func) | 6h | High | In Progress | 04 Mar | 04 Mar |  |  |  |  | Split by Items
14 | 🔵 Combine Bills Merge two open table bills into one | Dev 2 (Func) | 6h | High | In Progress | 04 Mar | 05 Mar |  |  |  |  | Combine Bills
FUNCTIONALITY — Dev 2
15 | 🟠 Discount & Promotions % or fixed amount discount at checkout | Dev 2 (Func) | 16h | High | Planned | 05 Mar | 07 Mar | [5 empty] | Discount & Pro
16 | 🟠 Live Activity Logs Real-time manager view of order activity | Dev 2 (Func) | 6h | Medium | Planned | 07 Mar | 08 Mar | [7 empty] | Live Activity
17 | 🟠 Bill Transfer Move items between two open bills | Dev 2 (Func) | 5h | Medium | Planned | 08 Mar | 08 Mar | [8 empty] | Bill Transfer
RECEIPT PRINTING — Both Developers
18 | 🟠 Receipt & Order Printing Customer receipt + kitchen order ticket | Both | 20h | High | Planned | 05 Mar | 08 Mar | [5 empty] | Receipt & Orde
TESTING & HANDOFF — Both Developers
19 | 🟠 Payment & Billing Testing All payment flows verified end-to-end | Both | 6h | High | Planned | 03 Mar | 05 Mar |  |  |  | Payment & Bill
20 | 🟠 UI Testing – All Device Sizes Phone, Galaxy A9, large tablet | Both | 6h | High | Planned | 06 Mar | 08 Mar | [6 empty] | UI Testing – A
21 | 🟠 Testing & Bug Fixes | Both | 5h | High | Planned | 07 Mar | 08 Mar | [7 empty] | Testing & Bug
22 | 🟠 Client Demo & Handoff | Both | 4h | Critical | Planned | 08 Mar | 08 Mar | [8 empty] | Client Demo &
Dev 1 (UI) – Daily Hours | [7 empty] | 7h | 7h | 7h | 7h | 6h | 6h | 8h | 8h | 6h
Dev 2 (Func) – Daily Hours | [7 empty] | 8h | 8h | 8h | 7h | 8h | 8h | 8h | 8h | 7h
Sprint: 28 Feb – 8 Mar 2026 (9 days) ¦ Dev 1 (UI): 62h ¦ Dev 2 (Functionality): 70h ¦ Max 8h / dev / day ¦ Tasks: 9 in progress · 13 planned

## Test Cases
POS Application · QA Test Cases · Sprint Feb–Mar 2026
TC # | Test Name | Feature Area | Test Type | Result | What Is Verified
── MENU SETUP ─────────────────────────────────────────────────────────────────
TC-01 | Menu Categories Setup | Menu Management | Functional | PASS | Create 3 categories (Drinks, Mains, Starters) — visible in POS with correct grouping
TC-02 | Add Menu Items | Menu Management | Functional | PASS | 6 items added with name, price and category — all appear correctly in POS ordering screen
TC-03 | Modifier Groups | Menu Management | Functional | PASS | Modifier groups created with multiple options — displayed at checkout when item tapped
TC-04 | Assign Modifiers to Items | Menu Management | Functional | PASS | Modifiers linked to menu items — correct options appear when ordering that item
── ORDERING ────────────────────────────────────────────────────────────────────
TC-05 | POS – Portrait Mode | POS Ordering | End-to-End | PASS | Select table → tap item → choose modifier → add to cart → send to kitchen — all steps complete
TC-06 | POS – Landscape Mode | POS Ordering | End-to-End | PASS | Same order flow in landscape orientation — layout adjusts, no buttons cut off
TC-07 | Kitchen Display Flow | Kitchen | End-to-End | PASS | Order appears in kitchen → staff progresses status → order marked Served in Order Management
TC-08 | Cancel Order – Kitchen Sync | Kitchen / Orders | Functional | PASS | Cancelling an order removes it from kitchen display immediately
TC-09 | Kitchen Station Settings | Settings | Functional | PASS | Add, rename and delete kitchen stations — changes visible in kitchen display
TC-10 | Item Routing to Station | Kitchen / Menu | Functional | PASS | Setting a station on a menu item sends that item to the correct kitchen station
── PAYMENT ─────────────────────────────────────────────────────────────────────
TC-11 | Cash Payment | Payment | End-to-End | PASS | Served order → Pay → enter cash → change calculated → order marked Paid
TC-12 | Full Bill Pay via Bill Screen | Payment | End-to-End | PASS | Bill screen opened → Pay Full Bill tapped → payment confirmed → order Paid
TC-13 | Card Payment via Terminal | Payment | End-to-End | PASS | Card payment sent to payment terminal — approval received — order marked Paid
TC-14 | Terminal Save & Reconnect | Payment | Functional | PASS | Terminal details saved — after app restart terminal reconnects without re-entering IP
── SPLIT BILL ──────────────────────────────────────────────────────────────────
TC-15 | Split Equally – 2 Guests | Split Bill | End-to-End | PASS | Bill divided equally between 2 guests — each guest pays their share independently
TC-16 | Split Equally – 3 Guests | Split Bill | End-to-End | PASS | 3-way equal split — all 3 guests pay — order marked Paid when all confirmed
TC-17 | Split by Items | Split Bill | End-to-End | PASS | Specific items assigned to each guest — guests pay only for their items
TC-18 | Multiple Payment Methods | Payment | End-to-End | PASS | Single bill paid across multiple payment entries — total matched — order Paid
TC-19 | Split – Card + Cash | Payment | End-to-End | PASS | Card portion processed via terminal, cash portion applied — combined total confirmed, order Paid
── COMBINE BILLS ───────────────────────────────────────────────────────────────
TC-20 | Combine Two Bills | Billing | End-to-End | PASS | Combine Bills button → select another table's order → orders merged → source order closed
── DATA PERSISTENCE ────────────────────────────────────────────────────────────
TC-21 | Data Saved After App Restart | Data Storage | Functional | PASS | Force-close and reopen app — all orders, menu items, payment status restored
── RESPONSIVE UI ───────────────────────────────────────────────────────────────
TC-22 | Mobile Phone – All Screens | Responsive UI | UI Testing | PASS | All app screens checked on phone size — portrait and landscape, correct layout and no overflow
TC-23 | Small Tablet – Galaxy A9 | Responsive UI | UI Testing | PASS | All screens on Galaxy A9 tablet — correct grid columns, touch targets, sidebar behaviour
TC-24 | Large Tablet – 10 inch+ | Responsive UI | UI Testing | PASS | All screens on 10 inch tablet in landscape — side panel pinned, multi-column layout correct
Total: 24 test cases ¦ Passed: 24 ¦ Failed: 0 ¦ Pass Rate: 100% ✅

## Progress Summary
POS Application · Feature Status · 28 Feb – 8 Mar 2026
Feature | Status | Est. Hrs | Owner | Notes
── RESPONSIVE UI ──────────────────────────────────────────
Mobile Phone Layout | 🔵 In Progress | 14h | Dev 1 | Portrait & landscape – all screens
Small Tablet Layout (Galaxy A9) | 🔵 In Progress | 14h | Dev 1 | 600–799dp – all screens
Large Tablet Layout (10 inch +) | 🟠 Planned | 12h | Dev 1 | Landscape side-by-side panels
── UI IMPROVEMENTS ────────────────────────────────────────
POS & Order Screen Updates | 🟠 Planned | 8h | Dev 1 | Item grid, cart panel refinements
Area & Table Selection | 🟠 Planned | 4h | Dev 1 | Area tabs on table picker
Printer Screen UI | 🟠 Planned | 7h | Dev 1 | Print buttons & receipt preview
Final Polish & Review | 🟠 Planned | 3h | Dev 1 | Cross-device final check
── PAYMENT & BILLING ──────────────────────────────────────
Order Number Display Fix | 🔵 In Progress | 3h | Dev 2 | Order number on all screens
Cash Payment Flow | 🔵 In Progress | 7h | Dev 2 | Full flow with change calculation
Card Payment via Terminal | 🔵 In Progress | 7h | Dev 2 | Approval from payment terminal
Split Payment – Card + Cash | 🔵 In Progress | 7h | Dev 2 | Mixed payment on single bill
Split Equally (2 & 3 Guests) | 🔵 In Progress | 7h | Dev 2 | Per-guest equal share
Split by Items | 🔵 In Progress | 6h | Dev 2 | Items assigned per guest
Combine Bills | 🔵 In Progress | 6h | Dev 2 | Merge two open bills
── FUNCTIONALITY ──────────────────────────────────────────
Discount & Promotions | 🟠 Planned | 16h | Dev 2 | % or fixed at checkout
Live Activity Logs | 🟠 Planned | 6h | Dev 2 | Real-time log updates
Bill Transfer | 🟠 Planned | 5h | Dev 2 | Move items between open bills
── PRINTING ───────────────────────────────────────────────
Receipt & Order Printing | 🟠 Planned | 20h | Both | Customer receipt + kitchen ticket
── TESTING & HANDOFF ──────────────────────────────────────
Payment & Billing Testing | 🟠 Planned | 6h | Both | All payment flows verified
UI Testing – All Device Sizes | 🟠 Planned | 6h | Both | Phone, Galaxy A9, tablet
Testing & Bug Fixes | 🟠 Planned | 5h | Both | Cross-feature final fixes
Client Demo & Handoff | 🟠 Planned | 4h | Both | Walkthrough and sign-off